## Sheet1
Phase | Week | Day | Focus Area | Task (Technical) | DSA Problem | Resources/Notes
Phase 1: Foundations | Week 1 | Day 1 | Environment Setup | Install VS Code, Git, Black, Pylance. Create GitHub Repo 'medical-ai-core'. | Two Sum (HashMaps) | Video: VS Code for Python Devs
Phase 1: Foundations | Week 1 | Day 2 | Python OOP | Refactor a script into a Class. Learn __init__, __str__ methods. | Contains Duplicate (Sets) | Article: Python Classes vs Functions
Phase 1: Foundations | Week 1 | Day 3 | Data Formats | Learn DICOM structure. Install pydicom & nibabel. Read 1 DICOM file. | Valid Anagram (Freq Counter) | Docs: Pydicom User Guide
Phase 1: Foundations | Week 1 | Day 4 | Data Formats | Learn NIfTI structure. Convert a DICOM series to 1 NIfTI volume. | Maximum Subarray (Kadane) | Video: DICOM vs NIfTI
Phase 1: Foundations | Week 1 | Day 5 | Data Visualization | Use matplotlib to visualize 3 slices (Axial, Coronal, Sagittal) of a 3D scan. | Group Anagrams (HashMap) | Library: matplotlib.pyplot
Phase 1: Foundations | Week 1 | Day 6 | Weekly Review | Push code to GitHub. Add a README. Review DSA. | Review Week 1 Problems | -
Phase 1: Foundations | Week 1 | Day 7 | System Design Lite | Sketch: How are CT scans stored in a hospital? (PACS servers). | System Design Basics | Video: Intro to PACS/DICOM
Phase 1: Foundations | Week 2 | Day 8 | PyTorch Basics | Tensors vs Arrays. GPU checking. Basic Tensor operations. | Product of Array Except Self | Docs: PyTorch Blitz
Phase 1: Foundations | Week 2 | Day 9 | Custom Datasets | Create 'MedicalVolumeDataset' class inheriting from torch.utils.data.Dataset. | Top K Frequent Elements | Tutorial: PyTorch Custom Datasets
Phase 1: Foundations | Week 2 | Day 10 | Data Loading | Implement __getitem__ to load NIfTI files on demand. | Valid Sudoku | -
Phase 1: Foundations | Week 2 | Day 11 | Transforms | Implement basic resizing and normalization (0-1 scaling). | Longest Consecutive Sequence | -
Phase 1: Foundations | Week 2 | Day 12 | Dataloaders | Use DataLoader to batch images. Test batch shapes. | Valid Palindrome (2 Pointers) | -
Phase 1: Foundations | Week 2 | Day 13 | Review & Git | Commit 'Data Loader' module. Refactor code. | Review Week 2 Problems | -
Phase 1: Foundations | Week 2 | Day 14 | Math Refresh | Understand Dice Loss vs Cross Entropy mathematically. | 3Sum | Video: Loss Functions explained
Phase 1: Foundations | Week 3 | Day 15 | Intro to MONAI | Install MONAI. Run the 'Hello World' tutorial. | Container With Most Water | Docs: MONAI Core
Phase 1: Foundations | Week 3 | Day 16 | MONAI Transforms | Replace your manual transforms with MONAI (LoadImaged, Spacingd). | Best Time to Buy/Sell Stock | -
Phase 1: Foundations | Week 3 | Day 17 | 3D U-Net | Import MONAI's BasicUNet. Print the model summary. | Longest Substring Without Repeating | Paper: U-Net Architecture
Phase 1: Foundations | Week 3 | Day 18 | Training Loop | Write the training loop (Optimizer, Loss, Backprop) for 3D data. | Longest Repeating Char Replacement | -
Phase 1: Foundations | Week 3 | Day 19 | Validation Loop | Implement Dice Metric for validation. | Permutation in String | -
Phase 1: Foundations | Week 3 | Day 20 | Experiment Tracking | Install TensorBoard/MLFlow. Log loss curves. | Review Week 3 | -
Phase 1: Foundations | Week 3 | Day 21 | Debug Model | Overfit on a SINGLE image to check if model learns. | Trapping Rain Water (Hard) | -
Phase 1: Foundations | Week 4 | Day 22 | Full Training | Train on full Spleen Dataset (Medical Decathlon). | Valid Parentheses (Stack) | Dataset: MSD Spleen
Phase 1: Foundations | Week 4 | Day 23 | Hyperparameters | Tune Learning Rate and Batch Size. | Min Stack | -
Phase 1: Foundations | Week 4 | Day 24 | Inference Script | Write predict.py: Load model -> Predict -> Save Mask. | Evaluate Reverse Polish Notation | -
Phase 1: Foundations | Week 4 | Day 25 | Visualization | Overlay mask on original image and save as PNG. | Generate Parentheses | -
Phase 1: Foundations | Week 4 | Day 26 | Code Cleanup | Add docstrings. Make it look professional. | Daily Temperatures | -
Phase 1: Foundations | Week 4 | Day 27 | GitHub Polish | Write a professional README with screenshots. | Review Week 4 | -
Phase 1: Foundations | Week 4 | Day 28 | Buffer Day | Catch up on pending tasks. | Car Fleet | -
Phase 1: Foundations | Week 4 | Day 29 | Buffer Day | Catch up on pending tasks. | Largest Rectangle in Histogram | -
Phase 1: Foundations | Week 4 | Day 30 | PHASE 1 MILESTONE | COMPLETE: Spleen Segmentation Pipeline. | Review All Phase 1 DSA | -
Phase 2: GenAI & MLOps | Week 5 | Day 31 | LLM Basics | Understand Transformers, Tokens, Context Window. | Binary Search | Video: Andrej Karpathy LLM Intro
Phase 2: GenAI & MLOps | Week 5 | Day 32 | Local LLMs | Install Ollama. Run Llama-3 locally. | Search a 2D Matrix | Tool: Ollama
Phase 2: GenAI & MLOps | Week 5 | Day 33 | RAG Concept | Learn Retrieval Augmented Generation flow. | Koko Eating Bananas | Article: Pinecone RAG Guide
Phase 2: GenAI & MLOps | Week 5 | Day 34 | Vector DBs | Install ChromaDB. Create embeddings for a sample text. | Find Minimum in Rotated Sorted Array | -
Phase 2: GenAI & MLOps | Week 5 | Day 35 | LangChain/LlamaIndex | Connect LLM to Vector DB. | Search in Rotated Sorted Array | Docs: LangChain
Phase 2: GenAI & MLOps | Week 5 | Day 36 | Medical RAG | Ingest a PDF medical guideline into the DB. | Time Based Key-Value Store | -
Phase 2: GenAI & MLOps | Week 5 | Day 37 | Chatbot UI | Build a simple Streamlit UI for the RAG bot. | Review Week 5 | Library: Streamlit
Phase 2: GenAI & MLOps | Week 6 | Day 38 | Docker Intro | Install Docker. Learn Image vs Container. | Reverse Linked List | Video: Docker for Beginners
Phase 2: GenAI & MLOps | Week 6 | Day 39 | Dockerfile | Write Dockerfile for your Spleen Segmentation app. | Merge Two Sorted Lists | -
Phase 2: GenAI & MLOps | Week 6 | Day 40 | Docker Run | Build and Run your container locally. | Reorder List | -
Phase 2: GenAI & MLOps | Week 6 | Day 41 | FastAPI Basics | Hello World API. Learn Pydantic models. | Remove Nth Node From End of List | Docs: FastAPI
Phase 2: GenAI & MLOps | Week 6 | Day 42 | Inference API | Create POST /predict endpoint for 3D Segmentation. | Copy List with Random Pointer | -
Phase 2: GenAI & MLOps | Week 6 | Day 43 | Integration | Test API with Postman/cURL. | Add Two Numbers | -
Phase 2: GenAI & MLOps | Week 6 | Day 44 | Docker Compose | Spin up API + Database using Compose. | Linked List Cycle | -
Phase 2: GenAI & MLOps | Week 7 | Day 45 | AWS Setup | Create Free Tier Account. Set up CLI. | Find the Duplicate Number | -
Phase 2: GenAI & MLOps | Week 7 | Day 46 | ECR | Push your Docker Image to AWS Elastic Container Registry. | LRU Cache | -
Phase 2: GenAI & MLOps | Week 7 | Day 47 | EC2/Lambda | Deploy the container on EC2 or Lambda. | Invert Binary Tree | -
Phase 2: GenAI & MLOps | Week 7 | Day 48 | CI/CD Concepts | What is GitHub Actions? Basic YAML config. | Maximum Depth of Binary Tree | -
Phase 2: GenAI & MLOps | Week 7 | Day 49 | Auto-Test | Write a PyTest case for your API. | Diameter of Binary Tree | -
Phase 2: GenAI & MLOps | Week 7 | Day 50 | Review | Ensure Cloud deployment works. | Balanced Binary Tree | -
Phase 2: GenAI & MLOps | Week 7 | Day 51 | System Design | Design: Scalable Medical Image Storage. | Same Tree | Ref: System Design Primer
Phase 2: GenAI & MLOps | Week 8 | Day 52 | GenAI + Vision | Intro to Vision Transformers (ViT). | Subtree of Another Tree | -
Phase 2: GenAI & MLOps | Week 8 | Day 53 | Multimodal | Concept: How to combine Image + Text (CLIP). | Lowest Common Ancestor of BST | -
Phase 2: GenAI & MLOps | Week 8 | Day 54 | Project 2 Start | Initialize 'Medical RAG Chatbot' Repo. | Binary Tree Level Order Traversal | -
Phase 2: GenAI & MLOps | Week 8 | Day 55 | Project 2 Code | Finalize RAG Pipeline. | Binary Tree Right Side View | -
Phase 2: GenAI & MLOps | Week 8 | Day 56 | Project 2 API | Wrap RAG in FastAPI. | Count Good Nodes in Binary Tree | -
Phase 2: GenAI & MLOps | Week 8 | Day 57 | Project 2 UI | Streamlit Frontend. | Validate Binary Search Tree | -
Phase 2: GenAI & MLOps | Week 8 | Day 58 | Project 2 Done | Document and Push to GitHub. | Kth Smallest Element in a BST | -
Phase 2: GenAI & MLOps | Week 8 | Day 59 | Buffer | Catch up. | Construct Binary Tree from Preorder/Inorder | -
Phase 2: GenAI & MLOps | Week 8 | Day 60 | PHASE 2 MILESTONE | COMPLETE: Cloud Deployed API & RAG Chatbot. | Review All Phase 2 DSA | -
Phase 3: Job Hunt | Week 9 | Day 61 | Resume Rewrite | Highlight: MONAI, Docker, RAG, AWS. | Kth Largest Element in a Stream | Action: Use 'STAR' method
Phase 3: Job Hunt | Week 9 | Day 62 | LinkedIn | Update Headline. Post about your Project. | Last Stone Weight | -
Phase 3: Job Hunt | Week 9 | Day 63 | Portfolio Site | Create a simple GitHub Pages site linking your projects. | K Closest Points to Origin | -
Phase 3: Job Hunt | Week 9 | Day 64 | Mock Interview 1 | Self-Record: 'Tell me about yourself'. | Kth Largest Element in an Array | -
Phase 3: Job Hunt | Week 9 | Day 65 | System Design | Design a Rate Limiter. | Task Scheduler | -
Phase 3: Job Hunt | Week 9 | Day 66 | System Design | Design Instagram (Photo Storage). | Design Twitter | -
Phase 3: Job Hunt | Week 9 | Day 67 | Apply Tier 2 | Apply to 5 'Safe' companies. | Review Heap/Priority Queue | -
Phase 3: Job Hunt | Week 10 | Day 68 | Graph Theory | BFS/DFS Revision. | Number of Islands | -
Phase 3: Job Hunt | Week 10 | Day 69 | Graph Algo | Dijkstra's Algorithm. | Max Area of Island | -
Phase 3: Job Hunt | Week 10 | Day 70 | Deep Learning Qs | Prepare: 'Explain ResNet', 'Explain Attention'. | Clone Graph | -
Phase 3: Job Hunt | Week 10 | Day 71 | Behavioral | Prepare answers for conflict/challenges. | Walls and Gates (or Rotting Oranges) | -
Phase 3: Job Hunt | Week 10 | Day 72 | Mock Interview 2 | Peer interview (Pramp or friend). | Pacific Atlantic Water Flow | -
Phase 3: Job Hunt | Week 10 | Day 73 | Apply Tier 1 | Apply to Google, Microsoft, GE, Siemens. | Surrounded Regions | -
Phase 3: Job Hunt | Week 10 | Day 74 | Review | Analyze Rejections/Feedback. | Review Graphs | -
Phase 3: Job Hunt | Week 11 | Day 75 | Adv DP | Climbing Stairs / Cost (Easy DP). | Climbing Stairs | -
Phase 3: Job Hunt | Week 11 | Day 76 | Adv DP | House Robber. | House Robber | -
Phase 3: Job Hunt | Week 11 | Day 77 | Adv DP | Longest Palindromic Substring. | Longest Palindromic Substring | -
Phase 3: Job Hunt | Week 11 | Day 78 | Network Qs | HTTP vs HTTPS, REST vs gRPC. | Palindromic Substrings | -
Phase 3: Job Hunt | Week 11 | Day 79 | SQL Basics | Revise SELECT, JOIN, GROUP BY. | Decode Ways | -
Phase 3: Job Hunt | Week 11 | Day 80 | Apply | Apply to 5 more companies. | Coin Change | -
Phase 3: Job Hunt | Week 11 | Day 81 | Buffer | Catch up. | Maximum Product Subarray | -
Phase 3: Job Hunt | Week 12 | Day 82 | Review All | Full review of Resume/Projects. | Word Break | -
Phase 3: Job Hunt | Week 12 | Day 83 | Final Polish | Ensure GitHub repos are green (active). | Longest Increasing Subsequence | -
Phase 3: Job Hunt | Week 12 | Day 84 | Mock Interview 3 | Full loop (Coding + System Design). | Unique Paths | -
Phase 3: Job Hunt | Week 12 | Day 85 | Relax/Focus | Focus on strongest skill. | Longest Common Subsequence | -
Phase 3: Job Hunt | Week 12 | Day 86 | Apply Aggressive | Cold Email Recruiters. | Review DP | -
Phase 3: Job Hunt | Week 12 | Day 87 | Keep Learning | Read a new paper (e.g., MedSAM). | Insert Interval | -
Phase 3: Job Hunt | Week 12 | Day 88 | Keep Learning | Read about Federated Learning. | Merge Intervals | -
Phase 3: Job Hunt | Week 12 | Day 89 | Keep Learning | Read about Explainable AI (SHAP). | Non-overlapping Intervals | -
Phase 3: Job Hunt | Week 12 | Day 90 | GOAL | You are now a Top 5% Candidate. | Meeting Rooms II (or similar) | -